## Slide 1
JOPACC · DA&BI INTERNSHIP
Exploring JoPACC Public Data
Warm-up exercise — prerequisite to the Executive Monthly Report (EMR) project
Team: Emam · Karmah · Naser
1 / 6

## Slide 2
PART 1
The Task, in General
Build fluency in JoPACC's own public payment-system data before EMR requirements begin
Act as a support layer to the data team — not just extracting numbers, but analyzing the analysis
Goal: return evidence-based proposals — new ideas, alterations, fixes to how reporting works
Systems in scope: CliQ, JoMoPay, eFAWATEERcom, ACH, ECCU
Two layers at once: build a clean 24-month dataset and use that process to judge JoPACC's own reporting
Ground rules
Public reports only — no internal or PDPL-sensitive data
Every figure
Cited by report month & source, reconciled to the source PDF
Audiences we serve
Risk, Compliance, and BusOps each read the same numbers differently
Definition of done
Explain what JoPACC publishes & summarize two years of trends by system
Task Overview
2 / 6

## Slide 3
PART 2
The Steps
1
Gather
Download 24 months of reports → Report library
2
Inventory
List metrics by system & granularity → Data dictionary
3
Structure
Transcribe into one tidy table → Clean dataset
4
Explore
Chart trends, MoM/YoY, system mix → Trend charts
5
Map to EMR
Tag Risk / Compliance / BusOps → Audience map
6
Present
Insights, quality notes, open questions → Readout
Suggested timing: ~2 weeks · we are wrapping up Step 3
3 / 6

## Slide 4
PART 3
Our Progress
Yearly
Fully extracted
Quarterly
Fully extracted
Monthly
8 months left
Split by report type: Emam (yearly) · Karmah (quarterly) · Naser (monthly)
Extraction via Claude AI + Python, following a shared standard
Reconciled through regular review meetings
Three separate datasets so far — validation & deduplication next
Role split originally by workload — familiarity with each report type grew through the work itself
Progress
4 / 6

## Slide 5
PART 3, CONTINUED
The Problems We Faced
Assumed the data was already clean
Skipped defining a real extraction standard — reports looked clean on the surface
Deceptively clean output
Looked like a proper table — but was noisy, inconsistent, and unreliable underneath
All three report types at once
Monthly, quarterly, yearly extracted together — ignored their structural differences
Fix: went back to the source
Re-studied structure → built Extraction Standard v3.1 with a controlled vocabulary
The trigger:
Problem only became visible once we tried to actually use the data
Root cause → Standard v3.1
5 / 6

## Slide 6
NEXT STEPS
Where We Go From Here
1
Wrap up cleaning — validate & deduplicate all three datasets
2
Finish the remaining 8 months of monthly extraction
3
Start identifying gaps — feeding directly into Step 5 (Map to EMR)
4
Turn findings into concrete proposals for the data team — the original goal of this task
Thank you
6 / 6